## SUM
Project Name / Project Number / PM | LSC SOLS Collaborative Classroom / 2012-22810 / Bill Johns | [7 empty] | *
Account Number: | WB11031 & IV6 4028
Date Created - Project Type: | 02/16/12 - General Renovation
Supplemental: | No
Provisions:
Capital Category:
| Appropriated Budget | Budget Adjustments | Adjusted Budget | Encumbered | Expensed | Anticipated Costs |  | Uncommitted Budget | Func Code
Land Acquisition
Land Acquisition | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | CLAC
Subtotal Land Acquisition Cost | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Construction Costs
New Construction Shell/Core | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | CCON
Renovation | 270759.43 | 0 | 270759.43 | 0 | 270759.43 | 0 |  | 0 | CREN
Special Fixed Equipment | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | CSFE
Site Development / Utilities Extensions | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | CSDV
Landscaping / Signage | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | CPKL
Permits | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | CPKL
Demolition | 19214.06 | 0 | 19214.06 | 0 | 19214.06 | 0 |  | 0 | CDEM
Hazardous Materials Abatement / Testing | 14268.48 | 0 | 14268.48 | 0 | 14268.48 | 0 |  | 0 | CHMA
Subtotal Construction Cost | 304241.97 | 0 | 304241.97 | 0 | 304241.97 | 0 |  | 0
Consultants
Construction Mgr | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | CCMG
Architect / Engineer | 43229.17 | 0 | 43229.17 | 0 | 43229.17 | 0 |  | 0 | CARE
Surveys and Tests | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | CSRT
Other | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | COTH
Subtotal Consultant Cost | 43229.17 | 0 | 43229.17 | 0 | 43229.17 | 0 |  | 0
Additional University Costs
FF & E | 67613.44 | 0 | 67613.44 | 0 | 67613.44 | 0 |  | 0 | CFFE
IT / Telecommunications | 82762.02 | 0 | 82762.02 | 0 | 82762.02 | 0 |  | 0 | CTCE
AV (Audio Visual) | 85800.66 | 0 | 85800.66 | 0 | 85800.66 | 0 |  | 0 | CTCE
Security | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | CTCE
Move-in Costs | 7061 | 0 | 7061 | 0 | 7061 | 0 |  | 0 | CMIC
Printing/Advertisement/Misc Admin | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | CADM
Parking Replacement Reserve | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | PKRS
Facilities Support (FACMAN PO's Only) | 1503.01 | 0 | 1503.01 | 0 | 1503.01 | 0 |  | 0 | CFSP
Subtotal Addl. University Cost | 244740.13 | 0 | 244740.13 | 0 | 244740.13 | 0 |  | 0
Contingency Funds
Contingency, Design Phase | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Contingency, Constr Phase | 3410.26 | -3410 | 0.26 | 0 | 0 | 0 |  | 0.26
Subtotal Contingency | 3410.26 | -3410 | 0.26 | 0 | 0 | 0 | 0 | 0.26
Fees
Project Management Cost ( 5 % ) | 29670.135 | 0 | 29670.135 | 0 | 29670.14 | -0.005 |  | 0 | CPMF
FS Fees ( 0.15 % ) | 890.1041 | 0 | 890.1041 | 0 | 890.1 | 0.00405 |  | 0 | FSPM
EH&S Fees ( 0.21 % ) | 1246.15 | 0 | 1246.15 | 0 | 1246.15 | 0 |  | 0 | EHSF
Purchasing Fees ( 0.30 % ) | 1780.21 | 0 | 1780.21 | 0 | 1780.21 | 0 |  | 0 | PSPC
State Risk Mgt Ins ( 0.34 % ) | 1191.43 | 0 | 1191.43 | 0 | 1191.43 | 0 |  | 0 | STRK
*Subtotal Fees ( 6 % Total ) | 34778.0291 | 0 | 34778.0291 | 0 | 34778.03 | -0.00095 | 0 | 0
TOTALS | 630399.5591 | -3410 | 626989.5591 | 0 | 626989.3 | -0.00095 | 0 | 0.26
[6 empty] | Funding Source A/O (145,400) IV6 4028 = |  | 0.26 | 03-19-13 MV
[6 empty] | Funding Source A/O (484,999.56) WB1 1031 = |  | 0 | 03-19-13 MV
[6 empty] | Advantage VS Project Budget Report Recon (Advantage less Totals E and F) |  | -0.00095
| *Fees are estimated at 98% of actual rate to be conservative* |  |  |  |  | Total Budget Amount To Date |  | 630400
Budget Transactions
1) A/O setup with $15,000 customer funded LM1 1016 on 2/23/12 (KL)
2) A/O increased by $430K ($300K LM1 1016 & $130K LM1 1001) for a new budget total of $445,000 4/17/12 JM
3) A/O setup with $128,000 for a total project budget of $573,000 4/17/12 JM
4) A/O increased by $40K to WB1 1031 (FY13) on 6/27/12 (JM)
| 5) A/O increased by $17,400 to IV6-4028 7/20/12 (PL) |  |  |  | 630,399.56 Actual | 593402.7
6) Financially closed 12/26/13, funding returned to source EH
Note on A13: Vendor Example: Holder Construction Group LLC
Note on O13: Vendor Example: Holder Construction Group LLC
Note on A14: Includes street repairs and parking lots. Vendor Examples: 3D INTL, Core Construction Srvs of AZ, Maloy Plumbing, JCCR Electric, MES Contracting, SDB INC, Parking
Note on O14: Includes street repairs and parking lots. Vendor Examples: 3D INTL, Core Construction Srvs of AZ, Maloy Plumbing, JCCR Electric, MES Contracting, SDB INC, Parking
Note on A15: Vendor Examples: Technology Providers Inc, VWR
Note on O15: Vendor Examples: Technology Providers Inc, VWR
Note on A16: Vendor Examples: Southwest Gas Corp
Note on O16: Vendor Examples: Southwest Gas Corp
Note on A17: Any expenses related to signage and landscaping. Includes Irrigation.
Note on O17: Any expenses related to signage and landscaping. Includes Irrigation.
Note on A18: Vendor Examples: Maricopa County Air Quality, City of Tempe, City of Phoenix
Note on O18: Vendor Examples: Maricopa County Air Quality, City of Tempe, City of Phoenix
Note on A19: Includes Asbestos demolition. Vendor Examples: Maloy Plumbing, Mes Contracting, SDB Inc.
Note on O19: Includes Asbestos demolition. Vendor Examples: Maloy Plumbing, Mes Contracting, SDB Inc.
Note on A20: Vendor examples: Adams and Wendt, Argus Contracting LLC, Fiberquant Analytical Services, Native environmental
Note on O20: Vendor examples: Adams and Wendt, Argus Contracting LLC, Fiberquant Analytical Services, Native environmental
Note on A24: Vendor Example: JS Waltz Construction LLC
Note on O24: Vendor Example: JS Waltz Construction LLC
Note on A26: Includes giotechnical, archaeological and soil testing.
Note on O26: Includes giotechnical, archaeological and soil testing.
Note on A27: Interior Design, Special Consultant, Asbestos Consultant.
Note on O27: Interior Design, Special Consultant, Asbestos Consultant.
Note on A31: Furniture, Fixtures & Equipment, includes cost of moving furniture too. Examples: ASUStores: Furniture, Bookstore (computers), Goodman's, Target
Note on O31: Furniture, Fixtures & Equipment, includes cost of moving furniture too. Examples: ASUStores: Furniture, Bookstore (computers), Goodman's, Target
Note on A32: Vendor Examples: Qwest, Tech Fee
Note on O32: Vendor Examples: Qwest, Tech Fee
Note on A33: Vendor Example: Audio Video Resources
Note on O33: Vendor Example: Audio Video Resources
Note on A34: Vendor Examples: Henry Bros Electronics Inc, ISAAC System
Note on O34: Vendor Examples: Henry Bros Electronics Inc, ISAAC System
Note on A35: Vendor Examples: Dircks Moving, EZ Moving and Cleaning, Graebel
Note on O35: Vendor Examples: Dircks Moving, EZ Moving and Cleaning, Graebel
Note on A36: Vendor Example: Tribune
Note on O36: Vendor Example: Tribune
Note on A38: Examples: FACMAN, POLYFACMAN, DPCFACMAN
Note on O38: Examples: FACMAN, POLYFACMAN, DPCFACMAN
Note on A42: Funds waiting to be allocated
Note on A43: Funds waiting to be allocated
Note on A47: Fee Calculated = 5 % * 98% * Total Budget Amt
Note on O47: Fee Calculated = 5 % * 98% * Total Budget Amount
Note on A48: Fee Calculated = 0.15 % * 98% * Total Budget Amt
Note on O48: Fee Calculated = 0.15 % * 98% * Total Budget Amount
Note on A49: Fee Calculated = 0.21 % * 98% * Total Budget Amt
Note on O49: Fee Calculated = 0.21 % * 98% * Total Budget Amount
Note on A50: Fee Calculated = 0.30 % * 98% * Total Budget Amt
Note on O50: Fee Calculated = PM 0.30 % * 98% * Total Budget Amount
Note on A51: Fee Calculated = 0.34 % * 98% * Total Budget Amt
Note on O51: Fee Calculated = 0.34 % * 98% * Total Budget Amount

## NOTES
FUNDING | YES | NO | Details
ABOR Approval Required:
CDP Approval
PI
PA
Funded from bundled bond pot:
Funding rules:
Funding Source | x |  | FY 12 Minor Cap
PROCESSING | YES | NO | Details
Supplemental Provisions Required
Pay ap requires Architects approval
In pre-construction
(if yes no notary required)
Special Accounting: ie vintage; moving
Check Pick-Up
Authorized pick-up by:

## SDB
SDB Inc. - JOC Contract |  |  |  | Project Number: 2012-22810
Simple Invoicing |  |  |  | Project Name: LSC SOLS Collaborative Classroom
No Schedule of Values Required (Optional on JOC) |  |  |  | Contract Party: SDB Inc
Retainage Amount (Optional on JOC) |  |  |  | Contract No: 918-11-004
No architecht Signature required (Optional on JOC) |  |  |  | Maricopa County JOC
RX WB10200059 - SC 17112M00133
PO Amt
|  | SD Crane | 220981
|  | Change Order #1 | 2085
|  | Change Order #2 | 12869
|  | PO Total | 235935
Invoices
Pay App 1 | 57429 | -5742.9 | 51686.1
Pay App 2 | 143536 | -14353.6 | 129182.4
Pay App 3 | 34970 | -3497 | 31473
Pay App 4 |  | 23593.5 | 23593.5
Total | 235935 | 0 | 235935
|  | Remaining to Bill | 0

## CLAC
LAND ACQUSITION | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
LAND ACQUISITION TOTAL | 0 |  |  |  | Total Expenses | 0 |  | Total Encumbrances | 0

## CCON
NEW CONSTRUCTION SHELL/CORE | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
NEW CONSTR SHELL TOTAL | 0 |  |  |  | Total Expenses | 0 |  | Total Encumbrances | 0

## CREN
RENOVATION | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
CARPET 6-28-12 MV | 13153.1 |  | PO WB102000087 | SCF174 | 2012-08-16 | 17324.43 | JM
CO#1 7/18/12 KL | 4171.33
17324.43
DALE MALOY 6-28-12 MV | 15300 | WB102000063 | SC 16113M00016 | 571 | 2012-07-10 | 15300 | MV
JOHN H WRIGHT 7/26/12 KL | 2200 |  | PV IV602000088 | 2012/113 | 2012-07-26 | 2200 | KL
SD CRANE 5-25-12 MV | 220981 | WB10200059 | SC 17112M00133 | PAY APP 1 | 2012-07-05 | 51686.1 | MV
CO#1 7/16/12 KL | 2085 |  |  | PAY APP 2 | 2012-08-30 | 129182.4 | KL
CO#2 8/23/12 KL | 12869 |  |  | PAY APP 3 | 2012-10-04 | 31473 | KL
|  | 235935 |  | PAY APP 4 | 2012-10-04 | 23593.5 | KL
[7 empty] | 235935 | 0
RENOVATION TOTAL | 270759.43 |  |  |  | Total Expenses | 270759.43 |  | Total Encumbrances | 0

## CSFE
SPECIAL FIXED EQUIPMENT | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
SPECIAL FIXED EQUIP TOTAL | 0 |  |  |  | Total Expenses | 0 |  | Total Encumbrances | 0

## CSDV
SITE DEVELOPMENT | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
SITE DEVELOPMENT TOTAL | 0 |  |  |  | Total Expenses | 0 |  | Total Encumbrances | 0

## CPKL
LANDSCAPING TOTAL | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
LANDSCAPE TOTAL | 0 |  |  |  | Total Expenses | 0 | Total Encumbrances | 0
PARKING TOTAL | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
PERMIT TOTAL | 0 |  |  |  | Total Expenses | 0 | Total Encumbrances | 0

## CDEM
DEMOLITION | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
JCCR ELECTRIC 5/3/12 KL | 317.75 |  | PV IV602000079 | 5/1/12 | 2012-05-03 | 317.75 | KL
JOHN H WRIGHT 4/23/12 KL | 14501.65 | IV602000128 | SC 24112M00613 | 2012-106 | 2012-05-17 | 14501.65 | MV
JOHN H WRIGHT 4/23/12 KL | 1356.68 |  | PV IV602000097 | 2012.114 | 2012-08-30 | 1356.68 | MV
JOHN H WRIGHT 8/29/12 KL | 237.98 |  | PV IV602000095 | 2012/116 | 2012-08-29 | 237.98 | KL
MALOY PLUMBING 5/9/12 KL | 2800 |  | PV IV602000081 | 529 | 2012-05-09 | 2800 | KL
DEMOLITION TOTAL | 19214.06 |  |  |  | Total Expenses | 19214.06 |  | Total Encumbrances | 0

## CHMA
HAZARD MATERIALS ABATEMENT | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
ADAMS & WENDT 4/18/12 KL | 3430 | IV602000124 | SC 15112M00143 | 4380 | 2012-06-12 | 3232.5 | KL
close adj | -197.5
3232.5
ARGUS 04-27-12 MV | 10079.76 | IV602000130 | SC 15112M00166 | 878047 | 2013-10-16 | 10675.98 | MV
CO#1 6/6/12 KL | 1499.76
close adj 11-7-13 | -903.54
10675.98
FIBERQUANT 8/28/12 KL | 360 |  | PV IV602000094 | 201202568 | 2012-08-28 | 360 | KL
HAZARD MATERIALS TOTAL | 14268.48 |  |  |  | Total Expenses | 14268.48 | Total Encumbrances | 0

## CCMG
CONSTRUCTION MANAGER | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
CCMG TOTAL | 0 |  |  |  | Total Expenses | 0 | Total Encumbrances | 0

## CARE
ARCHITECT/ENGINEER TOTAL | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
DICK & FRITSCHE DESIGN GROUP 2/23/12 KL | 10700 | WB102000057 | SC 15112M00118 | 19227 | 2012-04-30 | 10514.25 | KL
CO#1 4/18/12 KL | 32571 |  |  | 4.30.12 | 2012-05-08 | 25448.62 | KL
Close adj 7/2/13 | -41.83 |  |  | 19414 | 2013-01-15 | 7266.3 | JM
43229.17
ARCHITECT/ENG TOTAL | 43229.17 |  |  |  | Total Expenses | 43229.17 | Total Encumbrances | 0

## CSRT
SURVEY AND TESTS | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
SURVEYS/TESTS TOTAL | 0 |  |  |  | Total Expenses | 0 | Total Encumbrances | 0

## COTH
OTHER (INTERIOR DESIGN, SPECIAL CONSULTANTS) | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
OTHER TOTAL | 0 |  |  |  | Total Expenses | 0 | Total Encumbrances | 0

## CFFE
FIXED FURNITURE AND EQUIPMENT (FF & E) | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
DELL 5/8/12 KL | 1154.99 |  | PD LVPO5M31439 | XFW9PM9T3 | 2012-10-30 | 1200.05 | JM
Close adj 11/7/12 KL | 45.06
1200.05
DELL 11/7/12 KL | 54.29 |  | PV IV602000105 | XFW8N6N89 | 2012-11-07 | 54.29 | KL
GOODMAN'S INC 5/8/12 KL | 67233.9 | WB102000058 | SC 08112M00146 | 33633 | 2012-08-28 | 5460.13 | KL
Close Adj 7/2/13 | -874.8 |  |  | 35658 | 2012-12-12 | 60898.97 | JM
FF & E TOTAL | 67613.44 |  |  |  | Total Expenses | 67613.44 | Total Encumbrances | 0

## CTCE
IT / TELECOMMUNCATIONS | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
CENTURYLINK 4/19/12 KL | 21913.87 | IV602000125 | SC 02112M00159 | 70168972 | 2012-10-30 | 21913.87 | MV
HEWLETT PACKARD 5/14/12 KL | 56140.48 | IV602000133 | SC 02112M00171 | 51380377 | 2012-07-05 | 41.27 | MV
Close Adj 9/18/12 (TAX) | 4707.67 |  |  | 51363513 | 2012-07-05 | 1990.63 | MV
|  | 60848.15 |  | 51483547 | 2012-09-18 | 58816.25
[7 empty] | 60848.15 | 0
IX WB1IX000006
IT / TELECOM TOTAL | 82762.02 |  |  |  | Total Expenses | 82762.02 | Total Encumbrances | 0
AV (Audio Visual) | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
AUDIO VIDEO RESOURCES 6/7/12 KL | 16526.16 | WB102000062 | SC 02113M00001 | EO14616 | 2012-06-28 | 16526.16 | KL
KEARNEY ELECTRIC 6/7/12 KL | 3391.84 | IV602000141 | SC 24113M00075 | 1066793 | 2013-02-25 | 3391.84 | JM
TECHNOLOGY PROVIDERS, INC 6/7/12 KL | 65882.65 | WB102000061 | SC 02113M00002 | 19614 | 2012-09-12 | 65882.66 | KL
Close adj 9/12/12 KL | 0.01
65882.66
AV TOTAL | 85800.66 |  |  |  | Total Expenses | 85800.66 | Total Encumbrances | 0
SECURITY | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
SECURITY TOTAL | 0 |  |  |  | Total Expenses | 0 | Total Encumbrances | 0

## CMIC
MOVE-IN COSTS | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
DIRCKS MOVING 3/1/12 KL | 1393 |  | PD LVPO5M32645 | ASU120305-001 | 2012-04-27 | 1582 | MV
ADJ 04-27-12 MV | 189
1582
DIRCKS MOVING 4-27-12 MV | 2055 |  | PV IV602000078 | ASU120405-001 | 2012-04-27 | 2055 | MV
DIRCKS MOVING 7-6-12 MV | 3424 |  | PV WB102000016 | ASU120321-001 | 2012-07-06 | 3424 | MV
MOVE-IN COSTS TOTAL | 7061 |  |  |  | Total Expenses | 7061 | Total Encumbrances | 0

## CADM
PRINTING/ADVERTISEMENT/MISC ADMIN | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
PRINT/AD/MISC ADM TOTAL | 0 |  |  |  | Total Expenses | 0 | Total Encumbrances | 0

## PKRS
PARKING REPLACEMENT RESERVE | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
PKG REPLACEMENT TOTAL | 0 |  |  |  | Total Expenses | 0 | Total Encumbrances | 0

## CFSP
FACILITIES SUPPORT (LIST FACMAN PO'S ONLY) | [5 empty] | Summary Information
VENDOR NAME | ENCUMBRANCE | RX NUMBER | PO NUMBER | INVOICE # | DATE | AMOUNT PAID | ENTERED BY
FACMAN 5/29/12 KL | 3000 |  | PO IV602000074 |  |  | 619.2 | JM
Close Adj | -2380.8
(SWO 2012-033361)
Facman Internal Entry | 160 |  | IIP10090034 |  | 2013-05-26 | 160
Facman Internal Entry | 606.72 |  | IIP09180028 |  | 2013-05-26 | 606.72
Facman Internal Entry | 117.09 |  | IIP10010037 |  | 2013-05-26 | 117.09
FACILTIES SUPPORT TOTAL | 1503.01 |  |  |  | Total Expenses | 1503.01 | Total Encumbrances | 0

## CPMF
PROJECT MANAGEMENT COSTS |  | 2% |  |  |  | Summary Information
DESCRIPTION | AMOUNT |  | DOCUMENT NUMBER | ENTERED BY | DATE
PM FEES | 25.04 |  | JV PMF20120004 | KL | 2012-03-22
PM FEES | 5084.54 |  | JV PMF20120009 | KL | 2012-05-03
PM FEES | 24560.56 |  | JV FIN14001042 | EH | 2013-12-23
PROJECT MGMT TOTAL | 29670.14 |  | Project Mgt Fees - Pending | -0.005

## FSPM
FINANCIAL SERVICES FEES |  |  |  |  | Summary Information
DESCRIPTION | AMOUNT | DOCUMENT NUMBER | ENTERED BY | DATE
FS FEES | 34.48 | JV FIN13000270 | KL | 2012-08-14
FS FEES | 855.62 | JV FIN14001042 | EH | 2013-12-23
FIN SVCS FEE TOTAL | 890.1 | FIN SVCS Fees - Pending | 0.00405

## EHSF
EH&S FEES |  |  |  |  | Summary Information
DESCRIPTION | AMOUNT | DOCUMENT NUMBER | ENTERED BY | DATE
final ehs fee | 1246.15 | jv iv602000021 | jm | 2013-11-08
EH&S FEES | 1246.15 | EH&S Fees - Pending | 0

## PSPC
PURCHASING FEES |  |  |  |  | Summary Information
DESCRIPTION | AMOUNT | DOCUMENT NUMBER | ENTERED BY | DATE
PURCHASING FEES | 256.58 | JV PSP20120003 | KL | 2012-05-01
final purchasing fee | 1523.63 | jv iv602000022 | jm | 2013-11-08
PURCHASING FEES TOTTAL | 1780.21 | PURCHASING FEES - Pending | 0

## STRK
CONSTUCTION INSURANCE PREMIUM |  |  |  |  | Summary Information
DESCRIPTION | AMOUNT | DOCUMENT NUMBER | ENTERED BY | DATE
CONSTRUCTION PREM | 1.08 | JV $0504600009 | KL | 2012-05-04
CONSTRUCTION PREM | 6.99 | JV $0507600000 | KL | 2012-05-07
CONSTRUCTION PREM | 9.52 | JV $0511600007 | KL | 2012-05-11
CONSTRUCTION PREM | 86.53 | JV $0511600000 | KL | 2012-05-11
CONSTRUCTION PREM | 49.31 | JV $0518600009 | KL | 2012-05-18
CONSTRUCTION PREM | 10.99 | JV $0615600012 | KL | 2012-06-15
CONSTRUCTION PREM | 239.39 | jv $0720600000 | jm | 2012-07-20
CONSTRUCTION PREM | 7.48 | JV $0728600006 | KL | 2012-07-28
CONSTRUCTION PREM | 2.03 | JV $0831600014 | KL | 2012-08-31
CONSTRUCTION PREM | 4.61 | JV $0906600000 | KL | 2012-09-06
CONSTRUCTION PREM | 439.22 | JV $0907600000 | KL | 2012-09-07
CONSTRUCTION PREM | 187.23 | JV $1012600001 | KL | 2012-10-12
CONSTRUCTION PREM | 74.51 | JV $1010260000 | KL | 2012-11-02
CONSTRUCTION PREM | 11.53 | JV $0305600013 | MV | 2013-03-05
CONSTRUCTION PREM | 24.71 | JV $0118600000 | MV | 2013-01-18
CONSTRUCTION PREM | 36.3 | JV $1025600009 | JM | 2013-10-25
INSURANCE PREMIUM TOTAL | 1191.43 | Insurance Premium - Pending | 0

## Sheet2 (hidden)
Select One
Minor: = or < than $2M
Major: = or > than $2M
Shop = Prj exclusively handled internally
Select One
Yes
No